## Project - WRX120160
Date | Resource | Project Task | Entry Type | Hours | Site | Notes | Comments
2016-07-26 | Tester | rio_2015_plan_201505192 | Normal Hours | 1:00 |  |  | Timesheet entered successfully

## Data (hidden)
Tester | rio_2015_plan_201505192 | Normal Hours | Banasankari
| STAGE1 - PREPARATION & START-UP | Overtime Standard | Head Office
| TECHNICAL INFRASTRUCTURE | On Call | Whitfield
| Scope and plan Technical Infrastructure workstream and develop high level workstream activity plan | Subsistence
| Review Servelec documentation | Training
| Develop High Level Technical Infrastructure Strategy | Overtime Premium
| Review and approve High Level Technical Infrastructure Strategy | Public Holiday
High Level Technical Strategy Approved
End of Stage Review - Stage 1 2
Stage 1 - Preparation & Start-Up complete
STAGE 2 PRE-DEPLOYMENT PREPARATION
Interim Environment
Anonymistation script provided to Trust
IM Team run anonymisation script on MH and CH databases
Anonymised extracts ready for copy onto secure HDD
Change request to HP for copy of anonymised DB extracts from IM server in Wynyard Datacentre onto secure HDD and hand over to courier for onward transport to Servelec
HP copy extracts onto secure HDD and handover to courier for onward delivery to Servelec
Anonymised extracts of MH and CH data bases provided to Servelec
Servelec confirm delivery of anonymised extracts and load onto Interim Environment
Change request to HP to open up firewalls for connection to Interim Environment
Interim Environment remote installation & test)
Set up Mental Health & Community Health Instances (with BEH anonymised extracts)
Create Interim Environment Product Description (including Acceptance Criteria and Acceptance Testing)
Review & Approve Interim Environment Product Description (Trust)
Review & Approve Interim Environment Product Description (Servelec)
Interim Environment Product Description Document Approved
Create Interim Environment Approval Document
Sign Interim Environment Approval Document
Send Signed Interim Environment Approval Document to Servelec
Interim Environment complete
End of Stage Review - STAGE 2
Stage 2 - Pre-Deployment Preparation Complete
STAGE 3 - DESIGN
PLANNING & MANAGEMENT
BT Exit Meeting with HSCIC
Review Transition / Go Live options and costs (ie 'Lift and Shift' then Data Merge)
Develop options paper for review and decision
Decide Transition / Go Live option
Transition / Go Live option confirmed
Develop detailed plans for Stages 4, 5, 6 & 7 depending on preferred Transition / Go Live option
PLANNING & MANAGEMENT complete
TECHNICAL INFRASTRUCTURE
Technical Infrastructure Specification Design
Identify changes to WES to meet OpenRiO requirements
Create draft Technical Infrastructure specification
Conduct Technical Infrastructure specification review with HP Senior Technical Architect
Create NSSR for infrastructure changes
Technical Infrastructure Specification Design complete
High-Level HP Impact Assessment
Process NSSR for high-level Impact Assessment (IA)
Review HP IA
High-Level HP Impact Assessment & infrastructure costs ready for Board review
Detailed HP Impact Assessment
Update IA following review
Process NSSR for detailed Impact Assessment (IA)
Review HP IA
Detailed HP Impact Assessment & infrastructure costs ready for Board review
Review NSSR0288 by Board
NSSR0288 for OpenRio technical infrastructure signed off
Technical Infrastructure Specification Design complete
End of Stage Review - STAGE 3
STAGE 3 - DESIGN complete
STAGE 4 - DEVELOPMENT AND TESTING
Trust-wide Change Freeze
TECHNICAL INFRASTRUCTURE
TECHNICAL INFRASTRUCTURE - L&S Development
LIFT AND SHIFT HOSTED ENVIRONMENT
Provide all Trust's N3 router IP addresses for local break-out contingency
Obtain copy of databases & documents from BT
Load data and documents (Servelec)
Set up databases (Live, Test & Train Instances) (Servelec)
Connect Sandpit Spine (Spine2 DEP)
Hosted Environment Ready for Lift and Shift Testing
LIFT AND SHIFT WARRANTED ENVIRONMENT
Preparation
Provide HP with relevant build guides from Servelec
OpenRiO Icon Design
Create icons for OpenRiO 7
Review & sign-off icons with SM team
OpenRiO Icon Design complete
Provide icons to HP
Raise urgent Change Requests for URL access (FW, DNS)
Raise urgent Change Requests for Pilot
Raise urgent Change Requests for Full Deployment
Re-image UAT PCs x6
Identify pilot users for WES component testing
Request host names from pilot users
Pilot users' host names provided to HP ready for deployment
End User Communications
Agree comms strategy
Send out email comms to pilot users
Pilot User Communications complete
Development
WES Desktop Component Software Packaging
Manual installation of changes
Complete documentation (DIGS) for area of change
Package icon/shortcut
Package DropZone reg keys
WES Desktop Component Software Packaging ready for testing
Trust Print Server Upgrade - Dry Run
Implement Trust Printer Server configuration changes
Test Trust Printer Server configuration changes
Roll-back Trust Printer Server configuration changes
Update Trust Print Server Upgrade documentation
Trust Print Server Upgrade procedure proved
LIFT AND SHIFT WARRANTED ENVIRONMENT - Development ready for testing
TECHNICAL INFRASTRUCTURE - L&S Development complete
TECHNICAL INFRASTRUCTURE - L&S Testing
System Testing
Network Connectivity Testing - Hosted Environment
LIVE Servelec URL Testing
Availability of LIVE servers confirmed by Servelec
Test network connectivity to Servelec hosted environment - LIVE
DR Servelec URL Testing
Availability of DR servers confirmed by Servelec
Test network connectivity to Servelec hosted environment - DR
Network Connectivity Testing completed
Model Office (HP Internal) Testing
Test Deployment & roll-back of WES component updates
MO testing completed & ready for UAT
System Testing complete
User Acceptance Testing - WES Components
Perform UAT of Lift & Shift WES components - IM&T
UAT of WES components signed off - Project Team
Pilot UAT Testing
Deploy WES update packages to pilot PCs
Perform UAT of Lift & Shift WES components - pilot users
User Acceptance Testing - WES Components completed
Stage 4 Development and Testing Complete
STAGE 5 - LIFT AND SHIFT CUTOVER AND GO LIVE
TECHNICAL INFRASTRUCTURE
WES Deployment
End User Communications - L&S Go-Live
Agree comms & send to HP
Screen saver comms?
Send out Comms to all users
End User Communications - L&S Go-Live complete
Deploy WES update packages to BEH estate
WES deployment device testing
Send HPCA deployment stats - daily by email
Review WES component deployment with Service Line champions - weekly
WES deployment device testing checkpoint - week1
WES deployment device testing checkpoint - week2
WES deployment device testing checkpoint - week3
WES deployment device testing checkpoint - week4
WES deployment device testing checkpoint - week5
WES deployment device testing complete
Review deployment progress at weekly project meeting with HP
WES Infrastructure upgrades deployed ready for L&S Go-Live
Lift and Shift Cutover Go-Live
Trust Print Server Upgrade
Upgrade Trust Print Server configuration
UVT testing of batch printing
Trust Print Server UVT signed off
Trust Print Server ready for Go-Live
Confirm Go Live
Go live with Lift and Shift
Remove BT RiO Desktop Icons
Remove BT RiO program group & icons
Provide HPCA reports for removing BT RiO icons
BT RiO Desktop Icons removed
Stage 5 Lift and Shift Cutover and Go Live Complete
STAGE 6 - DATA MERGE
DATA MERGE TESTING & TECHNICAL INFRASTRUCTURE
DEVELOPMENT - WES Infrastructure Updates for Merge
NSSR for HP Changes
Raise NSSR for new desktop shorcuts & print server change
Develop NSSR IA & delivery approach
Approve NSSR for new desktop shorcuts & print server change
NSSR for HP Changes signed off
Preparation - WES Updates for Merge
NSSR288 - BT RiO icons removed
Create icon for Merge
Provide technical information to Comms Lead
Merge database instance stood up for WES infra testing
UAT PCs ready for testing
Preparation - WES Updates for Merge complete
WES Desktop Component Software Packaging for Merge
Complete documentation (DIGS) for area of change
Package icon/shortcut
WES Merge shortcut packaging ready for testing
DEVELOPMENT - WES Infrastructure Updates for Merge complete
TESTING - WES Infrastructure Updates for Merge
WES Merge Shortcut Testing
Test shortcut package deployment in Model Office
Test shortcut package deployment to UAT PCs
Test shortcut connectivity on UAT PCs
WES Merge Shortcut Testing complete
Trust Print Server Upgrade - Dry Run for Merge
Implement Trust Printer Server configuration changes
Test Trust Printer Server configuration changes
Roll-back Trust Printer Server configuration changes
Update Trust Print Server Upgrade documentation
Trust Print Server Upgrade procedure proved
TESTING - WES Infrastructure Updates for Merge
DEPLOYMENT - WES Merge Shortcut
Deploy WES Merge shortcut / icon to Trust estate
Device testing at Trust sites
DEPLOYMENT - WES Merge Shortcut deployed ready for merge cutover
Ready for Merge Cutover
End of Stage Review - STAGE 6
STAGE 6 - MERGE TESTING complete
STAGE 7 - MERGE CUTOVER & GO LIVE
Merge Cutover
Remove end-user access to MH & CH databases
Remove OpenRiO single dB instance desktop icons
Remove OpenRiO icons
OpenRiO single dB instance desktop icons removed
Trust Print Server Upgrade
Upgrade Trust Print Server configuration
System test Trust Print Server
UVT testing of batch printing
Trust Print Server UVT signed off
Trust Print Server ready for Go-Live
Ready for Go Live*
Merge Go-Live
Confirm Data Merge Go Live
Data Merge Go-Live complete
STAGE 7 - MERGE CUTOVER & GO LIVE complete
STAGE 8 - DEPLOYMENT VERIFICATION
Go-Live Support
Monitor & review deployment verification period against agreed criteria
Complete Deployment Verification Report
Review and approved Deployment Verification Report
Deployment Verification Report Signed Off
Confirm Go Live Verification period completed against agreed criteria
Go Live Verification (30 days from Ready for Go Live) complete